## Slide 1
KEC International Limited
Seekh Improvement #001 – Special Towers Framework (521)
Power T & D
Cables
Railways
Civil
Solar
Oil & Gas Pipelines

## Slide 2: M521 review cycle
Timeline 1: 14 weeks of back-and-forth on what SEC asked at Rev 0. Timeline 3: Rev 4 converged with contract completion.
TIMELINES
TIMELINE 1 · Complied with SEC interpretation on the 4th cycle
KEC Stance
SEC Stance
Multi-pier design +
RQD averaging
Rev 0
13-Jan-26
Comments Rev 0
Flags RQD avg +
pile-length assumptions
Defends RQD avg via
geotech letter
Rev 1
~Feb
NOT COMPLIED
Flags safety-case
framing
Regroups G1/G2;
shear partial
Rev 2
~early-Mar
Partial
Shear method
still questioned
Argues shear
non-critical for OHTL
Rev 3
~early-Apr
NOT COMPLIED
2 items NOT COMPLIED
— unfactored shear
Redesigned w/
FACTORED SHEAR
Rev 4
22-Apr-26
Pending approval
Awaiting decision
SITE EVENTS
4–5 Apr · Site cuts rebar at 1A/31 (bar-through-pile clash)
TIMELINE 2 Started Late
Contract start
6-Nov-2024
Rev 0 submitted
13-Jan-2026
~62 wks (~14 mo)
Rev 1 / 2 / 3
Feb–early-Apr
+~12 wks
Rev 4 filed
22-Apr-2026
~76 wks total
Contract completion
22-Apr-2026
⚠ same day
SEC COMMENTS (Rev 0) · complied at · days from comment receipt
SEC comment at Rev 0
Complied at
Days from receipt
RQD averaging — use POOREST borehole, not group-averaged (TES-P-122.06)
Rev 4 (22-Apr-26)
≈ 82 days
Unfactored shear on G1 + G2 — use FACTORED shear per ACI 318M
Rev 4 (22-Apr-26)
≈ 82 days
Pile-length assumptions need geotech-backed rework
Rev 2 (~early-Mar)
≈ 35 days
Notes: BACK-AND-FORTH MATH — speaker reference:
• ~62 wks (~14 months) from 6-Nov-2024 kick-off → 13-Jan-2026 Rev 0 submission for special towers — engineering window largely consumed BEFORE the first submission
• 14 wks Rev 0 → Rev 4 (4 revisions on the same core questions: RQD averaging, factored shear, rebar cutting authority)
• ~76 wks (~17.5 months) total from kick-off to Rev 4. Rev 4 date coincides with contract completion — zero construction runway.
WHAT SEC ASKED AT REV 0 vs WHAT LANDED AT REV 4:
• RQD: SEC said use poorest borehole. KEC averaged until Rev 4.
• Shear: SEC said factored per ACI 318M. KEC argued non-critical until Rev 4.
• Bar cutting: SEC said no cut without Designer + Approved-Designer letter. Still being closed via revised Jawda letter.
Every one of SEC's positions cited TES-P-122.06 / ACI 318M — not reviewer preference.
TIMELINE 2 (Site + Jawda Track) + SOW II–VI checklist are in back-up slides at the end.

## Slide 3: Learnings — what happened, how we close it
LESSONS
WHAT HAPPENED → CORRECTIVE ACTION
What happened on M521
Corrective action
Constructability
▸ Design identifies special towers at tower-spotting freeze
▸ Design reviews constructability on draft drawings (12-point)
▸ PM verifies Rev 0 before release
Rev 0 → Rev 4 took 14 weeks
Rev 4 converged on SEC's Rev 0 position.
▸ SEC's preferred interpretation in Rev 0 for special towers (explore AI use cases)
Foundation work on special towers began late
▸ Special towers tracked separately in Primavera P6
▸ Front-load special-tower foundations along with the suspension batch
No first-of-its-kind verification was run for F-AN3/SPL.
▸ BIM / digital-twin clash-check on cage geometry, or
▸ Full-scale rebar mockup (borrowed from oil & gas practice)
Site cut rebar at 1A/31
▸ Strengthen Quality process to flag non-conformances

## Slide 4: Constructability Check + Earmark Process for Special Towers
CONSTRUCTABILITY
STEP 1 — IDENTIFY · which towers get the special track, and when we earmark them
FLAG AS SPECIAL IF ANY:
▸ F-AN3/SPL, F-DE, large-angle / "SPL" variant ▸ Deviation > 45° ▸ RQD < 25 in any critical layer, or rock interface < 3 m
▸ Non-spread foundation (pile / multi-pier / raft) ▸ First-of-its-kind ▸ Sabkha, wadi crossing, sloped ground
EARMARK AT TOWER-SPOTTING FREEZE
(Month 1–3) — when tower types are
assigned in the schedule
STEP 2 — REVIEW · 12-point Constructability Checklist (signed item-by-item, pre-IFC)
1
Every bottom longitudinal bar crosses a pile footprint ← the 1A/31 miss
2
≥ 50 mm clear spacing between bars at pier edge
3
Top bars survive stub cutout without cutting
4
Development length Ld achievable at pier-to-pad
5
Bar bend points clear of stub flanges
6
Vibrator-diameter clearance between bars
7
Chair-bar spacing matches pile-cap depth
8
Temperature reinforcement in open pad area
9
Uplift-test pullout points accessible + instrumented
10
Formwork matches pier geometry; no reshaping at site
11
Construction sequence diagram shipped with drawing
12
No site cutting long-span bars (TES-P-122.06 · ACI 315/318)
STEP 3 — EXECUTE · post-earmark workflow - what we do after a tower is flagged
When
Action
AS-IS on M521 (what didn't happen)
Month 1
Design IDENTIFIES — flag at tower-spotting freeze; separate line in Primavera P6
F-AN3/SPL not earmarked; entered the special track late
Month 2
Design REVIEWS constructability — 12-point check on draft drawings
No constructability review; bar-through-pile on Rev 0 was not caught
Month 3–4
SUBMIT — Foundation Plan & Details to SEC (with risk-flag package)
Rev 0 for special towers filed 13-Jan-26, ~62 weeks (~14 months) after 6-Nov-24 kick-off
Month 5
PM VERIFIES Rev 0 — mandatory risk-flagging sheet signed
No single PM-owned verification; risks surfaced one revision at a time
Parallel
AMBITIOUS — BIM clash-check OR full-scale rebar mockup (first-of-its-kind)
Neither attempted; Stage D never run for F-AN3/SPL
Execution
Monthly Seekh review until first pile-cap poured; site changes auto-flag
1A/31 clash surfaced from the 1v1 on TSE release-risks — no NCR was raised

## Slide 5
THANK YOU
Global Footprint in
110+ countries*
*Includes EPC and Supply
www.kecrpg.com
Registered Office
RPG House, 463, Dr. Annie Besant Road, Worli, Mumbai - 400 030.
Phone: +91-22-6667 0200 Email: kecindia@kecrpg.com
Follow us on:

## Slide 6: Back-up · SOW 24CO375 Foundation Checklist — sections II to VI
TES-P-122.06 · TCS-P-122.05/.21 · TCS-Q-113.03 · ACI 318M · IEEE 691-2001 · ASTM D1586/D2113/D3689
BACK-UP
II. FOUNDATION DESIGN
SOW Cl 5.11 · TES-P-122.06 · ACI 318M
▸ Design per ACI 318M + TES-P-122.06 — torsion, uplift, compression, shear, moments
▸ Type: drilled pier / spread / rock anchor / rock pier / driven pile
▸ Grouped towers: use POOREST borehole — no averaging
▸ Top 1.0 m soil EXCLUDED from uplift / compression / lateral
▸ Spread footing FoS ≥ 1.5 on uplift; OLF per Table-2
▸ Sabkha: 13 mm permanent steel casing, rebar hot-dip galv
III. SOIL INVESTIGATION
SOW Cl 6.21
▸ COMPANY-approved geotech; start after prelim proposal approval
▸ Borehole at EACH tower; depth ≥ (pier + 3 m) OR 10 m
▸ ASTM D1586 (SPT) + D2113 (diamond core drilling)
▸ FoS ≥ 3 on ALL soil parameters; COMPANY interprets
▸ ≥3 boreholes with 2″ PVC piezometers, depth ≥3 m
IV. REINFORCEMENT
SOW Cl 6.03 · TCS-P-122.05 · TCS-P-122.21
▸ Reinforcement + tie wire per TCS-P-122.05 / TES-P-122.06
▸ Tie wire 1.5 mm, 2 wraps + twists; 2 separate spliced ties
▸ WWF per ASTM A496 / SASO 224; fy ≥ 240 MPa
▸ Stub-angle bond per TCS-P-122.21; coal-tar + mastic tape
▸ No site cutting long-span bars without design authority
V. PROTOTYPE UPLIFT TEST — PRE-CONSTRUCTION GATE
SOW Cl 5.12
▸ Full-scale test: 1 tangent + 1 heavy-angle, BEFORE production
▸ Prototype design gated on APPROVED soil report
▸ COMPANY witnesses; contractor pays access
▸ Jacks / load cells / dial gauges calibrated w/ COMPANY
▸ Per ASTM D-3689-90 quick-load method
VI. CONSTRUCTION QUALITY CONTROL
SOW Cl 4.87 · 6.02 · 6.25
▸ Checklists define HOLD / WITNESS / SURVEILLANCE
▸ Pre-pour inspection mandatory; request → COMPANY
▸ Cover 85 ± 10 mm to tie outside; design 95 mm
▸ CIP concrete per TCS-Q-113.03 + TCS-P-122.05
▸ Inspection logbook; results stored / retrievable
KEY GATES — what stops the line if missed
cross-cuts the five sections
▸ No averaged RQD across grouped towers — use poorest
▸ Soil APPROVED before prototype design starts
▸ Uplift test (1 tangent + 1 heavy-angle) BEFORE production
▸ No long-span bar cutting without design authority
▸ Pre-pour HOLD request to COMPANY
▸ Drawings + material: only after IFC, certified + dated
GATE: no IFC, no material — until II–VI are signed off on project-specific soil data.

## Slide 7: Back-up · 12-point Constructability Checklist — each item explained
Plain-language meaning + source (ACI / TES-P / SOW clause) for every checkpoint. A synthesis, not a published list.
BACK-UP
1
Bottom longitudinal bar crosses a pile footprint
Every bottom longitudinal bar must be routed so its path crosses the footprint of at least one pile; otherwise the bar cannot transfer tower load and is structurally dead. The 1A/31 failure was bars exiting the pier edge without crossing a pile.
1A/31 failure mode itself
2
≥ 50 mm clear spacing between bars at pier edge
50 mm is the practical OHTL-foundation minimum because a 40–55 mm poker vibrator needs clearance to consolidate concrete between bars. Tighter = honeycombing = a hidden defect.
ACI 318 §25.2
3
Top bars survive the stub cutout without cutting
The top reinforcement mat has a cutout to let the vertical stub pass. Top bars near that cutout must be routed so they do not need to be cut at site; if cut, they lose structural function at the cutout zone.
ACI 315/318 · TES-P-122.06
4
Development length Ld achievable at pier-to-pad
At the transition from narrow pier to wide pad, bars change direction (L-hooks / 90° bends). Each bar must have enough straight length + bend to reach full Ld before termination; else the bar pulls out under load.
ACI 318 §25.4
5
Bar bend points clear of stub flanges
Tower stubs carry horizontal flange plates. A bar bend-radius arc must not clash with a flange; if it does, placement is impossible without shop-cutting the flange — 3D clash must be checked before drawing goes IFC.
Pre-IFC 3D clash check
6
Vibrator-diameter clearance between bars
Immersion concrete vibrators are ~50 mm diameter. Bars must allow vibrator insertion throughout the cage depth; congestion leaves un-vibrated concrete pockets — voids / capacity loss invisible from outside.
Site constructability
7
Chair-bar spacing matches pile-cap depth
Chair bars hold the upper mat at design elevation during the pour. Spacing must be calibrated to cap depth and steel weight — too wide = mat deflects and ends up at wrong elevation; too tight = congestion.
Rebar placement practice
8
Temperature reinforcement in open pad area
Large open concrete areas need nominal reinforcement to control cracking from thermal contraction + shrinkage, independent of structural load. Easy to miss in OHTL drawings because load concentrates at piers, not pad.
ACI 318 §24.4
9
Uplift-test pullout points accessible + instrumented
SOW §5.12 mandates a full-scale uplift test on one tangent + one heavy-angle prototype. The prototype must have physical anchor points for hydraulic jacks + dial gauges designed into the rebar layout — afterthought = drilled post-cure = compromised test.
SOW 24CO375 §5.12
10
Formwork matches pier geometry; no reshaping at site
Formwork must be fabricated to match design pier geometry exactly (tapered, multi-step). If site must cut / rework formwork to fit the drawing, dimensional accuracy of the finished concrete and rebar cover suffers.
Site constructability
11
Construction sequence diagram shipped with drawing
Shows order of operations: excavation → lean concrete → bottom mat → chair bars → top mat → stub setting → formwork → pour → cure. Without it, each crew interprets differently and sequence errors cascade into rebar conflicts like 1A/31.
Standard OHTL drawing practice
12
No site cutting of long-span bars
Longitudinal bars carry the primary structural load; cutting them at site without design authority is prohibited. If a bar does not fit, the drawing must be revised and re-approved before placement proceeds. This was the SEC-consultant flag at 1A/31.
TES-P-122.06 · ACI 315/318

## Slide 8: Back-up · Site + Jawda Track (parallel to the SEC cycle in April)
The day-by-day scramble on the 1A/31 fix — back-up detail for the Timeline-1 story on the front page.
BACK-UP
TIMELINE 2 · Site + Jawda Track · April 2026
4–5 Apr
Site cuts rebar 1A/31
(bar-through-pile)
9 Apr
Faisal (Technotran):
service-moment justification
13–16 Apr
Zafery chases Jawda
6× over 5 days
16 Apr
Jawda letter issued —
generic, needs rework
19 Apr
1v1 on TSE release-risks:
2 gridlocked, 2 retrofit
24 Apr
Concrete pour scheduled
(pending revised letter)
POSITIONS · KEC solution · SEC stance · why the Jawda letter needs a re-issue
KEC SOLUTION (current path):
▸ 2-vs-2 fix split. 1A/31 + 1B/31 on site-cut + Faisal service-moment + revised Jawda letter.
▸ 1A/32 + 1B/32 on clean retrofit (+2.3 T extra rebar). Rev 4 with factored shear filed 22-Apr.
SEC STANCE (consistent across 14 weeks):
▸ No unfactored shear on OHTL foundation reinforcement (ACI 318M).
▸ No averaged RQD where individual layers read 0 or < 10.
▸ No rebar cutting without Designer + Approved-Designer letter (TES-P-122.06).
WHY THE 16-APR JAWDA LETTER NEEDS A RE-ISSUE:
▸ Generic scope — did not name all 4 locations. Did not address top-bar cutting at the stub.
▸ Wrong factor-of-safety framing. Needed further markup; still being closed as of 23-Apr.
▸ Revised letter to align with the 19-Apr 4-point site-feasibility proposal before the pour.